# CommuniCare Website Modernization Project Plan

Static, Accessible Website Hosted on GitHub Pages

Prepared for Cumberland County Innovation & Technology Services and CommuniCare

| Item | Project Baseline |
| --- | --- |
| Hosting | GitHub Pages |
| Source Control | GitHub repository |
| Site Type | Static HTML output with CSS, JavaScript, images, and public documents |
| Accessibility Target | WCAG 2.2 Level AA |
| Custom Domain | cccommunicare.org and/or www.cccommunicare.org, subject to final DNS decision |
| Content Classification | Public website content only |
| Backend | None in the base project |
| Database | None in the base project |
| Sensitive Data Collection | Not permitted in the static site |
| Project Schedule | TBD after scope and content approval |

Important scope decision: This plan replaces the earlier server-hosted .NET design with a static GitHub Pages architecture. IIS, a DMZ web server, .NET runtime hosting, Entity Framework, and SQL Server are not required for the base website. If CommuniCare later requires secure referrals, authentication, databases, protected uploads, or other server-side processing, those functions must be designed as a separate application or approved external service.

# 1. Document Control

| Field | Value |
| --- | --- |
| Document | CommuniCare Website Modernization Project Plan |
| Version | 1.0 |
| Architecture | Static website published through GitHub Pages |
| Prepared by | Cumberland County ITS |
| Client | CommuniCare |
| Status | Planning baseline |
| Dates | TBD |
| Project manager | TBD |
| Technical lead | TBD |
| CommuniCare content owner | TBD |
| Security / accessibility reviewers | TBD |

## 1.1 Change Control

Any change that introduces server-side processing, a database, protected information, authentication, online payments, referral intake, file uploads containing non-public information, or a third-party form processor must be treated as a scope and architecture change. The change must be reviewed before implementation.

# 2. Executive Summary

The existing CommuniCare repository contains a legacy ASP.NET Web Forms site, but the publicly used pages are predominantly static content: text, navigation, images, public documents, contact information, and links. The modernization therefore does not require a server-side application unless new requirements introduce dynamic or sensitive workflows.

The recommended approach is to rebuild the public website as a standards-based static site, store the source in GitHub, publish it with GitHub Pages, and map the existing CommuniCare domain to the published site. GitHub Actions will build and deploy the site. The site will be designed to meet WCAG 2.2 Level AA accessibility requirements and will include automated and manual accessibility testing before production release.

This approach reduces infrastructure and maintenance requirements while preserving professional development practices such as source control, pull requests, code review, automated testing, deployment history, rollback, and change tracking.

## 2.1 Business Outcomes

Replace the legacy fixed-width website with a modern responsive design.

Provide a mobile-first and accessible experience for the public.

Retain and improve all approved public information from the current site.

Make content and navigation easier to maintain.

Eliminate unnecessary IIS, .NET, database, and DMZ hosting dependencies for the public site.

Use GitHub as the source of truth for code, content, deployment, and change history.

Use GitHub Pages for low-cost static hosting.

Establish a controlled process that Cumberland County ITS can support under the CommuniCare SLA.

Keep the architecture ready for a future separate application if CommuniCare later needs secure transactions or workflows.

## 2.2 Recommended Technical Baseline

| Area | Recommended Baseline |
| --- | --- |
| Output | Static HTML5, CSS, JavaScript, images, fonts, and public documents |
| Build approach | Static site generator or component-based static build. Preferred option: Astro static output, subject to approval. |
| Repository | New modernization repository recommended. Legacy repository remains reference/archive. |
| Hosting | GitHub Pages |
| Deployment | GitHub Actions Pages workflow |
| Domain | Existing CommuniCare custom domain |
| HTTPS | GitHub Pages HTTPS enforcement |
| Accessibility | WCAG 2.2 Level AA target |
| Performance | Core Web Vitals and Lighthouse validation |
| SEO | Semantic HTML, metadata, sitemap.xml, robots.txt, canonical URLs |
| Analytics | TBD. Use only an approved analytics solution. |
| Forms | No sensitive or server-processed forms in base scope |

# 3. Scope

## 3.1 In Scope

Discovery and inventory of the current GitHub repository and currently published website.

Content review with CommuniCare to determine what is current, obsolete, duplicated, or missing.

Information architecture and navigation redesign.

Responsive visual redesign.

Accessible reusable page templates and components.

Migration of approved public text, links, images, and public documents.

Home, About, Programs/Services, Resources, Board/Leadership, Contact, HIPAA/Privacy information, Terms, and other approved informational pages.

Accessible document links and document inventory.

Search or filtering implemented client-side only if needed and appropriate.

Custom domain configuration for GitHub Pages.

HTTPS enforcement.

GitHub Actions build and deployment workflow.

Automated HTML, link, accessibility, and quality checks where practical.

Manual accessibility review.

User acceptance testing.

Production cutover and rollback plan.

Operations documentation and SLA support procedures.

## 3.2 Out of Scope Unless Formally Added

SQL Server or any other database.

IIS or County DMZ website hosting.

.NET 10, Blazor, Entity Framework, or Telerik UI for the base static site.

Authentication or client/staff portals.

Secure referral intake.

Collection or storage of PHI, PII, juvenile case data, court data, or other non-public information.

Server-side email processing.

Online payments.

Protected file uploads.

Case management or workflow processing.

Any integration requiring secrets to execute in the browser.

Static-site boundary: A static website can contain public content, links, embedded maps, accessible media, and client-side interaction. It cannot safely hold secrets or directly perform trusted server-side transactions. If a feature requires a secret, a trusted identity, or protected data storage, it belongs outside GitHub Pages.

# 4. Assumptions, Constraints, and Open Decisions

## 4.1 Confirmed Baseline

CommuniCare is a nonprofit organization supported by Cumberland County under an SLA.

The website content is intended to be public.

The current repository is available in GitHub.

The new site may be hosted through GitHub Pages.

The website must be designed for accessibility.

The existing public domain is expected to continue to be used.

## 4.2 Decisions That Must Be Confirmed

| ID | Decision | Options / Notes | Decision Owner | Status |
| --- | --- | --- | --- | --- |
| D-01 | New repository or reuse current repository | Recommended: new repository for the modern site; retain legacy repo as archive/reference. | TBD | Open |
| D-02 | Repository visibility | Public repository permits GitHub Pages on GitHub Free. Private Pages requires an eligible paid plan. | TBD | Open |
| D-03 | Static build technology | Preferred: Astro static output. Alternatives: plain HTML/CSS/JS, Jekyll, Eleventy, Hugo. | TBD | Open |
| D-04 | Primary hostname | cccommunicare.org, www.cccommunicare.org, or one redirecting to the other. | TBD | Open |
| D-05 | Analytics | None or approved analytics platform. | TBD | Open |
| D-06 | Public contact method | Phone/email only, mailto link, or approved third-party contact form. | TBD | Open |
| D-07 | Content owners | CommuniCare must identify who approves program, contact, legal, and document content. | TBD | Open |
| D-08 | Accessibility acceptance authority | Identify reviewer and final acceptance process. | TBD | Open |
| D-09 | Publishing approval | Define who can merge and who can approve production deployment. | TBD | Open |

# 5. Target Architecture

The base architecture contains no application server and no database. The browser downloads prebuilt files from GitHub Pages. Content changes are committed to GitHub, validated through pull requests and automated checks, then deployed through GitHub Actions.

| Layer | Component | Responsibility |
| --- | --- | --- |
| Authoring | Local workstation + Codex + Git | Create and review site code and content. |
| Source Control | GitHub repository | Version history, pull requests, reviews, issues, branch protection. |
| Build | GitHub Actions | Install dependencies if needed, build static files, run checks, publish artifact. |
| Hosting | GitHub Pages | Serve the static website. |
| DNS | Current DNS provider | Map CommuniCare domain to GitHub Pages. |
| TLS | GitHub Pages | Provide and enforce HTTPS for the custom domain after correct DNS configuration. |
| Monitoring | TBD | Uptime and broken-link monitoring. |
| Support | Cumberland County ITS | Maintain website under the SLA. |

## 5.1 Recommended Repository Structure

The exact structure may change after the static build technology is approved. The following structure is the recommended starting point.

### Repository structure reference

CCCommunicareModern/ .github/ workflows/ pages.yml quality.yml pull_request_template.md docs/ architecture.md content-inventory.md accessibility.md deployment.md operations.md src/ components/ layouts/ pages/ content/ styles/ scripts/ assets/ public/ documents/ images/ favicon/ robots.txt tests/ AGENTS.md README.md package.json .gitignore

# 6. GitHub Governance and Security

Because the website may be published from a public repository, assume everything committed to the repository is public. Public source does not grant write access. Only authorized collaborators can modify the repository. The primary security controls are identity security, repository permissions, protected branches, review requirements, and secure deployment configuration.

Require multi-factor authentication for all users with write or administrative access.

Minimize repository administrators.

Require pull requests before changes reach the production branch.

Disable direct pushes to the production branch where supported.

Require at least one approval before merge. Increase the number if the SLA or County process requires it.

Require status checks to pass before merge.

Require conversation resolution before merge.

Use CODEOWNERS if ownership boundaries are useful.

Do not store passwords, API keys, tokens, private certificates, internal-only configuration, or personal information in the repository.

Use least-privilege GitHub Actions permissions.

Pin or deliberately manage third-party GitHub Actions dependencies.

Enable Dependabot and code/security scanning if available and appropriate.

Verify the custom domain through GitHub to reduce domain takeover risk.

Do not use wildcard DNS records for the GitHub Pages domain.

# 7. Master Milestone Plan

| ID | Milestone | Outcome |
| --- | --- | --- |
| M0 | Project Initiation and Architecture Confirmation | Confirm static-site direction, governance, scope, owners, and approval path. |
| M1 | Repository and GitHub Controls | Create or prepare the repository and establish safe change/deployment controls. |
| M2 | Legacy Site Inventory | Inventory current pages, documents, images, links, orphaned files, and obsolete content. |
| M3 | Content and Requirements Validation | Obtain CommuniCare decisions on current content and new content. |
| M4 | Information Architecture | Design sitemap, navigation, URL scheme, page types, and content relationships. |
| M5 | Accessibility and Design System | Define WCAG requirements, reusable design tokens, components, and responsive behavior. |
| M6 | Static Site Foundation | Create the new static project, shared layout, build scripts, and local development process. |
| M7 | Core Navigation and Global Components | Implement header, navigation, footer, breadcrumbs, alerts, and global utility components. |
| M8 | Homepage | Build and approve the new homepage. |
| M9 | Program and Service Content | Build reusable content templates and migrate approved program/service pages. |
| M10 | Resources, Documents, and Public Information | Migrate public resources and improve document organization. |
| M11 | Contact and Location Experience | Create accessible contact/location pages without unsafe server-side processing. |
| M12 | SEO, Performance, and Metadata | Implement metadata, sitemap, robots, social previews, and performance optimization. |
| M13 | Automated Quality Gates | Add build, link, HTML, accessibility, and other automated checks. |
| M14 | GitHub Pages Deployment | Configure Actions deployment and a non-production preview/testing process. |
| M15 | Accessibility Validation and Remediation | Perform manual and automated WCAG 2.2 AA testing and remediate defects. |
| M16 | User Acceptance Testing | Conduct CommuniCare review, content signoff, and operational readiness review. |
| M17 | Domain, HTTPS, and Production Cutover | Configure custom domain, DNS, HTTPS, final deployment, and rollback readiness. |
| M18 | Post-Go-Live and SLA Operations | Monitor production, document support procedures, and establish ongoing content maintenance. |
| M19 | Legacy Retirement and Archive | Preserve legacy source as required and retire obsolete hosting only after successful stabilization. |

# 8. Detailed Milestones and Tasks

## M0 - Project Initiation and Architecture Confirmation

M0.1  Confirm in writing that the base website will be static and will contain public information only.

Deliverable: Approved architecture statement | Dependency: None | Owner: TBD

M0.2  Confirm that no current required feature depends on server-side .NET code, a database, authentication, protected uploads, or sensitive form processing.

Deliverable: Dynamic-functionality decision log | Dependency: M0.1 | Owner: TBD

M0.3  Confirm whether future referrals or forms are part of this project or explicitly excluded.

Deliverable: Scope decision | Dependency: M0.1 | Owner: TBD

M0.4  Identify Cumberland County ITS project lead and technical lead.

Deliverable: Named roles | Dependency: None | Owner: TBD

M0.5  Identify CommuniCare executive/content approver and page/content owners.

Deliverable: Approval matrix | Dependency: None | Owner: TBD

M0.6  Confirm repository ownership and GitHub account or organization where the modern site will live.

Deliverable: Repository ownership decision | Dependency: M0.1 | Owner: TBD

M0.7  Confirm repository visibility and GitHub plan requirements before relying on no-cost Pages hosting.

Deliverable: Hosting cost/plan confirmation | Dependency: M0.6 | Owner: TBD

M0.8  Confirm the domain owner, DNS provider, and who is authorized to change DNS.

Deliverable: DNS ownership record | Dependency: None | Owner: TBD

M0.9  Confirm accessibility target of WCAG 2.2 Level AA and identify acceptance reviewer.

Deliverable: Accessibility acceptance plan | Dependency: M0.1 | Owner: TBD

M0.10  Create project issue board, milestone tracker, and decision log.

Deliverable: Project tracking workspace | Dependency: M0.4 | Owner: TBD

### Codex Work Package M0

Do not modify production code. Read the repository and create docs/project-charter.md. Create docs/architecture-decision-static-github-pages.md. Document that the site is public-information-only and that backend features are outside base scope. Create docs/open-decisions.md with each unresolved decision marked TBD. Do not invent domain, owner, staff, or approval information. Commit documentation only.

## M1 - Repository and GitHub Controls

M1.1  Create a new modern repository or formally approve reuse of the existing repository.

Deliverable: Modern site repository | Dependency: M0.6 | Owner: TBD

M1.2  If a new repository is used, keep the legacy repository unchanged as the historical source during migration.

Deliverable: Legacy preservation approach | Dependency: M1.1 | Owner: TBD

M1.3  Create README.md with purpose, local setup, build, testing, and deployment instructions.

Deliverable: README.md | Dependency: M1.1 | Owner: TBD

M1.4  Create AGENTS.md containing architecture rules for Codex.

Deliverable: AGENTS.md | Dependency: M1.1 | Owner: TBD

M1.5  Create .gitignore appropriate to the selected static toolchain.

Deliverable: .gitignore | Dependency: M1.1 | Owner: TBD

M1.6  Configure branch protection/rules for the production branch.

Deliverable: Protected production branch | Dependency: M1.1 | Owner: TBD

M1.7  Require pull requests and status checks for production changes.

Deliverable: PR controls | Dependency: M1.6 | Owner: TBD

M1.8  Limit admin and write permissions to approved maintainers.

Deliverable: Permission review | Dependency: M1.1 | Owner: TBD

M1.9  Require MFA for users with write/admin access according to the account/organization capabilities.

Deliverable: Identity control confirmation | Dependency: M1.8 | Owner: TBD

M1.10  Create pull request and issue templates.

Deliverable: GitHub templates | Dependency: M1.1 | Owner: TBD

M1.11  Define release tags and rollback convention.

Deliverable: Release/version convention | Dependency: M1.1 | Owner: TBD

### Codex Work Package M1

Create the repository documentation and governance files only. Create AGENTS.md with these rules: - This is a static public website. - Do not add a server, database, authentication, API keys, or secrets. - Output must be deployable to GitHub Pages. - Accessibility target is WCAG 2.2 AA. - Use semantic HTML before ARIA. - All interactive elements must be keyboard accessible. - Do not copy obsolete ASP.NET, VB.NET, FrontPage, Telerik, or Web Forms code. - Preserve public content only after it is approved for migration. Create a pull_request_template.md with accessibility, responsive, links, and content-review checkboxes.

## M2 - Legacy Site Inventory

M2.1  Inventory all current repository files by type and location.

Deliverable: File inventory | Dependency: M1.1 | Owner: TBD

M2.2  Inventory all active navigation links from the current public pages.

Deliverable: Navigation inventory | Dependency: M2.1 | Owner: TBD

M2.3  Identify duplicate and dated page copies, backup files, and orphaned pages.

Deliverable: Legacy cleanup list | Dependency: M2.1 | Owner: TBD

M2.4  Identify pages that contain only static content.

Deliverable: Static-page inventory | Dependency: M2.1 | Owner: TBD

M2.5  Identify any page that contains form tags, server controls, legacy form handlers, or code-behind references.

Deliverable: Dynamic-marker inventory | Dependency: M2.1 | Owner: TBD

M2.6  Identify whether each dynamic-marker page is actually linked from the current public navigation.

Deliverable: Active vs orphaned dynamic page report | Dependency: M2.5 | Owner: TBD

M2.7  Inventory PDFs, PowerPoints, images, and other downloadable files.

Deliverable: Document/media inventory | Dependency: M2.1 | Owner: TBD

M2.8  Check each internal and external link and record broken or redirected links.

Deliverable: Link audit | Dependency: M2.2 | Owner: TBD

M2.9  Capture current URLs that should be preserved or redirected after launch.

Deliverable: URL migration map | Dependency: M2.2 | Owner: TBD

M2.10  Record current page titles, headings, metadata, and visible content for review.

Deliverable: Content inventory | Dependency: M2.2 | Owner: TBD

### Codex Work Package M2

Analyze the legacy repository without changing it. Generate docs/content-inventory.md. Generate docs/url-inventory.csv if practical. Classify each page as active, duplicate, archive, orphaned, or unknown. Classify each page as static or containing legacy dynamic markers. Do not assume a dynamic marker means the feature is active. Trace links from active navigation. List all documents and media separately. Flag broken links and content that appears dated, but do not delete or rewrite content.

## M3 - Content and Requirements Validation

M3.1  Review the inventory with CommuniCare and mark each page Keep, Rewrite, Merge, Archive, or Remove.

Deliverable: Approved content disposition | Dependency: M2 | Owner: TBD

M3.2  Identify new pages or content CommuniCare wants added.

Deliverable: New-content list | Dependency: M3.1 | Owner: TBD

M3.3  Identify current contact information, office hours, addresses, phone numbers, and approved public email addresses.

Deliverable: Approved contact data | Dependency: M3.1 | Owner: TBD

M3.4  Review program and service names, descriptions, eligibility information, and referral instructions.

Deliverable: Approved program content | Dependency: M3.1 | Owner: TBD

M3.5  Review board/staff content and determine whether names/photos should remain public.

Deliverable: Approved people content | Dependency: M3.1 | Owner: TBD

M3.6  Review HIPAA, privacy, terms, accessibility, and other policy/legal pages with the proper content owner.

Deliverable: Approved policy content | Dependency: M3.1 | Owner: TBD

M3.7  Review all public documents for currency and accessibility.

Deliverable: Approved document list | Dependency: M2.7 | Owner: TBD

M3.8  Determine whether any document should be converted to accessible HTML rather than retained as a PDF.

Deliverable: Document remediation plan | Dependency: M3.7 | Owner: TBD

M3.9  Approve final project scope before development starts.

Deliverable: Scope baseline | Dependency: M3.1-M3.8 | Owner: TBD

## M4 - Information Architecture

M4.1  Create the proposed sitemap based on approved content.

Deliverable: Sitemap | Dependency: M3.9 | Owner: TBD

M4.2  Design primary and secondary navigation.

Deliverable: Navigation model | Dependency: M4.1 | Owner: TBD

M4.3  Define page categories such as Home, Program, Resource, Standard Content, Policy, Contact, and Document Listing.

Deliverable: Page-type model | Dependency: M4.1 | Owner: TBD

M4.4  Define readable, stable URL patterns.

Deliverable: URL standard | Dependency: M2.9 | Owner: TBD

M4.5  Map every approved legacy URL to its new URL or removal disposition.

Deliverable: Redirect/migration matrix | Dependency: M4.4 | Owner: TBD

M4.6  Define breadcrumbs where useful.

Deliverable: Breadcrumb rules | Dependency: M4.2 | Owner: TBD

M4.7  Define footer structure and required legal/support links.

Deliverable: Footer model | Dependency: M4.2 | Owner: TBD

M4.8  Obtain CommuniCare approval of sitemap and navigation before full page development.

Deliverable: IA approval | Dependency: M4.1-M4.7 | Owner: TBD

## M5 - Accessibility and Design System

M5.1  Define design tokens for typography, spacing, borders, radii, and colors.

Deliverable: Design token specification | Dependency: M4.8 | Owner: TBD

M5.2  Validate all text/background combinations for required contrast.

Deliverable: Contrast matrix | Dependency: M5.1 | Owner: TBD

M5.3  Define visible keyboard focus styles.

Deliverable: Focus design | Dependency: M5.1 | Owner: TBD

M5.4  Define heading hierarchy rules and landmark structure.

Deliverable: Semantic HTML standard | Dependency: M5.1 | Owner: TBD

M5.5  Define link, button, card, alert, breadcrumb, navigation, footer, image, and document-link patterns.

Deliverable: Component specification | Dependency: M5.1 | Owner: TBD

M5.6  Define responsive breakpoints based on content behavior, not specific devices.

Deliverable: Responsive standard | Dependency: M5.1 | Owner: TBD

M5.7  Define image alt-text rules and decorative-image handling.

Deliverable: Image accessibility standard | Dependency: M5.1 | Owner: TBD

M5.8  Define reduced-motion behavior for any animation.

Deliverable: Motion accessibility standard | Dependency: M5.1 | Owner: TBD

M5.9  Define skip link, keyboard navigation, menu behavior, and mobile navigation accessibility.

Deliverable: Navigation accessibility standard | Dependency: M5.1 | Owner: TBD

M5.10  Create design prototypes for desktop and mobile views and obtain approval.

Deliverable: Approved visual direction | Dependency: M5.1-M5.9 | Owner: TBD

## M6 - Static Site Foundation

M6.1  Approve the static build technology.

Deliverable: Toolchain decision | Dependency: M0.7, M5.10 | Owner: TBD

M6.2  If Astro is approved, create an Astro project configured for static output and GitHub Pages compatibility.

Deliverable: Static project foundation | Dependency: M6.1 | Owner: TBD

M6.3  If another generator is selected, create an equivalent component/layout structure that emits plain static HTML.

Deliverable: Static project foundation | Dependency: M6.1 | Owner: TBD

M6.4  Implement base HTML document metadata, language, viewport, and character encoding.

Deliverable: Base document template | Dependency: M6.2 or M6.3 | Owner: TBD

M6.5  Implement global CSS reset/base styles and design tokens.

Deliverable: Global style layer | Dependency: M5 | Owner: TBD

M6.6  Create reusable layouts for standard pages and content detail pages.

Deliverable: Layout components | Dependency: M6.4 | Owner: TBD

M6.7  Create content collections/data structures if the selected tool supports them.

Deliverable: Structured content model | Dependency: M6.1 | Owner: TBD

M6.8  Create local build, preview, and validation commands.

Deliverable: Developer workflow | Dependency: M6.2 or M6.3 | Owner: TBD

M6.9  Document local setup for Visual Studio, VS Code, Codex, and command line usage as applicable.

Deliverable: Developer setup documentation | Dependency: M6.8 | Owner: TBD

### Codex Work Package M6

Read AGENTS.md and all approved architecture/design documents before changing code. Scaffold the approved static site generator with static output only. Do not add any server runtime, database, authentication, or backend API. Create reusable layouts and components. Use semantic HTML5. Use CSS custom properties for design tokens. Minimize JavaScript and use progressive enhancement. Create npm scripts or equivalent for dev, build, preview, test, lint, and accessibility checks. The build output must be a folder of static files suitable for GitHub Pages.

## M7 - Core Navigation and Global Components

M7.1  Build accessible site header and logo area.

Deliverable: Header component | Dependency: M6 | Owner: TBD

M7.2  Build desktop navigation.

Deliverable: Desktop nav | Dependency: M4.8, M6 | Owner: TBD

M7.3  Build mobile navigation with keyboard and screen-reader support.

Deliverable: Mobile nav | Dependency: M5.9, M7.2 | Owner: TBD

M7.4  Add skip-to-main-content link.

Deliverable: Skip link | Dependency: M5.9 | Owner: TBD

M7.5  Build breadcrumb component.

Deliverable: Breadcrumbs | Dependency: M4.6 | Owner: TBD

M7.6  Build site-wide footer.

Deliverable: Footer component | Dependency: M4.7 | Owner: TBD

M7.7  Build site alert/announcement component for public messages.

Deliverable: Announcement component | Dependency: M5.5 | Owner: TBD

M7.8  Build reusable CTA/button/link components or styles.

Deliverable: CTA component set | Dependency: M5.5 | Owner: TBD

M7.9  Test global components at keyboard-only and 200% zoom.

Deliverable: Global component accessibility test | Dependency: M7.1-M7.8 | Owner: TBD

## M8 - Homepage

M8.1  Confirm homepage content hierarchy and approved messaging.

Deliverable: Homepage content brief | Dependency: M3.9 | Owner: TBD

M8.2  Implement hero section with meaningful heading and primary actions.

Deliverable: Homepage hero | Dependency: M5.10, M7 | Owner: TBD

M8.3  Implement service/program discovery area.

Deliverable: Service discovery section | Dependency: M4 | Owner: TBD

M8.4  Implement featured information/resource area if approved.

Deliverable: Featured content section | Dependency: M3 | Owner: TBD

M8.5  Implement announcements area if approved.

Deliverable: Announcement placement | Dependency: M7.7 | Owner: TBD

M8.6  Implement partner/community section only if approved and current.

Deliverable: Partner section | Dependency: M3 | Owner: TBD

M8.7  Verify responsive layout from small mobile widths through large desktop.

Deliverable: Responsive homepage | Dependency: M8.2-M8.6 | Owner: TBD

M8.8  Run accessibility, performance, and content review before using the homepage design as the pattern for the remaining site.

Deliverable: Homepage approval | Dependency: M8.7 | Owner: TBD

## M9 - Program and Service Content

M9.1  Create reusable Program/Service template.

Deliverable: Program template | Dependency: M6, M7 | Owner: TBD

M9.2  Define consistent program fields such as summary, audience, services, contact, location, referral instructions, and related resources.

Deliverable: Program content schema | Dependency: M3.4 | Owner: TBD

M9.3  Migrate approved program pages from legacy content.

Deliverable: Migrated programs | Dependency: M9.1, M3.4 | Owner: TBD

M9.4  Rewrite only where CommuniCare has approved changes or where accessibility/readability requires structural improvement.

Deliverable: Approved revised content | Dependency: M3.4 | Owner: TBD

M9.5  Remove duplicate legacy navigation and repeated layout markup during migration.

Deliverable: Clean program pages | Dependency: M9.3 | Owner: TBD

M9.6  Add related content links where approved.

Deliverable: Related-content navigation | Dependency: M9.3 | Owner: TBD

M9.7  Review each program page with CommuniCare before final approval.

Deliverable: Program content signoff | Dependency: M9.3-M9.6 | Owner: TBD

## M10 - Resources, Documents, and Public Information

M10.1  Create resource listing pattern.

Deliverable: Resource component | Dependency: M6, M7 | Owner: TBD

M10.2  Group resources into approved categories.

Deliverable: Resource taxonomy | Dependency: M3.7 | Owner: TBD

M10.3  Migrate only approved current documents.

Deliverable: Document migration | Dependency: M3.7 | Owner: TBD

M10.4  Use descriptive link text rather than raw filenames or 'click here'.

Deliverable: Accessible document links | Dependency: M10.3 | Owner: TBD

M10.5  Show file type and size where useful.

Deliverable: Document metadata | Dependency: M10.3 | Owner: TBD

M10.6  Provide accessible HTML equivalents for high-value content where required or practical.

Deliverable: HTML content alternatives | Dependency: M3.8 | Owner: TBD

M10.7  Replace obsolete PowerPoint/PPS references where approved.

Deliverable: Updated resources | Dependency: M3.7 | Owner: TBD

M10.8  Test documents and resource navigation on mobile and with keyboard navigation.

Deliverable: Resource QA | Dependency: M10.1-M10.7 | Owner: TBD

## M11 - Contact and Location Experience

M11.1  Confirm approved address, postal address, phone, fax, email, office hours, and location details.

Deliverable: Contact content approval | Dependency: M3.3 | Owner: TBD

M11.2  Build accessible contact page using public contact information.

Deliverable: Contact page | Dependency: M11.1 | Owner: TBD

M11.3  If a map is embedded, ensure the page also provides the address and directions information in text.

Deliverable: Accessible location content | Dependency: M11.2 | Owner: TBD

M11.4  If email links are provided, use clear labels and approved public addresses.

Deliverable: Email links | Dependency: M11.1 | Owner: TBD

M11.5  Do not add a public form until the form processing, data classification, spam protection, privacy, and vendor/service approach are separately approved.

Deliverable: Form boundary documented | Dependency: M0.3 | Owner: TBD

## M12 - SEO, Performance, and Metadata

M12.1  Create unique page titles and descriptions.

Deliverable: SEO metadata | Dependency: M9-M11 | Owner: TBD

M12.2  Add canonical URLs after the final domain pattern is approved.

Deliverable: Canonical metadata | Dependency: D-04 | Owner: TBD

M12.3  Create Open Graph/social preview metadata.

Deliverable: Social metadata | Dependency: M12.1 | Owner: TBD

M12.4  Generate sitemap.xml.

Deliverable: Sitemap.xml | Dependency: M4, M12.1 | Owner: TBD

M12.5  Create robots.txt.

Deliverable: robots.txt | Dependency: M12.4 | Owner: TBD

M12.6  Optimize images and use responsive image techniques.

Deliverable: Optimized media | Dependency: M10 | Owner: TBD

M12.7  Lazy-load non-critical images where appropriate.

Deliverable: Image loading optimization | Dependency: M12.6 | Owner: TBD

M12.8  Minimize and bundle CSS/JavaScript as supported by the selected toolchain.

Deliverable: Optimized assets | Dependency: M6 | Owner: TBD

M12.9  Check for layout shift, oversized media, unnecessary scripts, and blocking assets.

Deliverable: Performance remediation | Dependency: M12.6-M12.8 | Owner: TBD

M12.10  Run Lighthouse or equivalent performance checks and document results.

Deliverable: Performance report | Dependency: M12.9 | Owner: TBD

## M13 - Automated Quality Gates

M13.1  Add build validation on pull requests.

Deliverable: PR build check | Dependency: M6 | Owner: TBD

M13.2  Add HTML validation or equivalent static output checks.

Deliverable: HTML quality check | Dependency: M6 | Owner: TBD

M13.3  Add internal link checking.

Deliverable: Link check | Dependency: M9-M11 | Owner: TBD

M13.4  Add accessibility automation such as axe/Pa11y/Lighthouse CI where supported.

Deliverable: Automated accessibility check | Dependency: M5 | Owner: TBD

M13.5  Add linting/formatting checks for the selected toolchain.

Deliverable: Code quality check | Dependency: M6 | Owner: TBD

M13.6  Add a check that fails on obvious secret patterns or use GitHub secret scanning where available.

Deliverable: Secret protection | Dependency: M1 | Owner: TBD

M13.7  Require these checks before merge to the production branch.

Deliverable: Protected quality gate | Dependency: M13.1-M13.6 | Owner: TBD

### Codex Work Package M13

Create a GitHub Actions workflow for pull-request quality checks. The workflow must not deploy pull requests to production. Run the static build. Run the project's lint and formatting checks. Run internal link checks. Run automated accessibility checks against built pages. Fail the workflow when required quality checks fail. Use least-privilege permissions. Document each check in docs/quality-gates.md.

## M14 - GitHub Pages Deployment

M14.1  Enable GitHub Pages for the approved repository.

Deliverable: Pages enabled | Dependency: M1, D-02 | Owner: TBD

M14.2  Choose GitHub Actions as the publishing source if a build process is used.

Deliverable: Publishing source | Dependency: M14.1 | Owner: TBD

M14.3  Create a Pages deployment workflow that builds the approved static site.

Deliverable: Pages workflow | Dependency: M6 | Owner: TBD

M14.4  Upload only the generated static artifact for deployment.

Deliverable: Deployment artifact | Dependency: M14.3 | Owner: TBD

M14.5  Configure Pages deployment permissions with least privilege.

Deliverable: Workflow permissions | Dependency: M14.3 | Owner: TBD

M14.6  Use the github-pages environment and production branch protections.

Deliverable: Deployment environment | Dependency: M14.3 | Owner: TBD

M14.7  Confirm successful deployment to the default GitHub Pages URL before custom-domain cutover.

Deliverable: Technical preview deployment | Dependency: M14.3-M14.6 | Owner: TBD

M14.8  Document deployment logs, rollback method, and how to redeploy a prior release.

Deliverable: Deployment runbook | Dependency: M14.7 | Owner: TBD

### Codex Work Package M14

Create .github/workflows/pages.yml using the current supported GitHub Pages deployment actions. Trigger production deployment only from the approved production branch and allow manual workflow dispatch if approved. Set permissions to contents: read, pages: write, id-token: write. Build the site into the approved static output directory. Upload the static output as the Pages artifact. Deploy using the github-pages environment. Do not deploy from pull-request events. Add clear comments and update docs/deployment.md.

## M15 - Accessibility Validation and Remediation

M15.1  Run automated WCAG checks across all production pages.

Deliverable: Automated a11y report | Dependency: M9-M14 | Owner: TBD

M15.2  Test the entire site using keyboard only.

Deliverable: Keyboard test results | Dependency: M15.1 | Owner: TBD

M15.3  Verify visible focus and logical focus order.

Deliverable: Focus review | Dependency: M15.2 | Owner: TBD

M15.4  Test navigation and representative pages with at least one screen reader.

Deliverable: Screen reader test results | Dependency: M15.1 | Owner: TBD

M15.5  Test at 200% browser zoom and narrow viewport reflow.

Deliverable: Zoom/reflow test | Dependency: M15.1 | Owner: TBD

M15.6  Verify heading hierarchy, landmarks, link purpose, alt text, labels, and language attributes.

Deliverable: Semantic review | Dependency: M15.1 | Owner: TBD

M15.7  Verify color contrast and non-color indicators.

Deliverable: Visual accessibility review | Dependency: M15.1 | Owner: TBD

M15.8  Review PDFs and downloadable documents in scope for accessibility issues.

Deliverable: Document accessibility review | Dependency: M10 | Owner: TBD

M15.9  Remediate all critical and high-severity accessibility issues before production approval.

Deliverable: Accessibility remediation | Dependency: M15.1-M15.8 | Owner: TBD

M15.10  Document known exceptions, if any, with owner, rationale, and remediation plan.

Deliverable: Accessibility exception register | Dependency: M15.9 | Owner: TBD

## M16 - User Acceptance Testing

M16.1  Provide CommuniCare the preview URL and UAT checklist.

Deliverable: UAT package | Dependency: M14, M15 | Owner: TBD

M16.2  Verify every approved page and program exists.

Deliverable: Content completeness check | Dependency: M16.1 | Owner: TBD

M16.3  Verify phone numbers, addresses, public email addresses, links, and documents.

Deliverable: Content accuracy check | Dependency: M16.1 | Owner: TBD

M16.4  Verify mobile, tablet, and desktop behavior.

Deliverable: Responsive UAT | Dependency: M16.1 | Owner: TBD

M16.5  Verify keyboard navigation and key accessibility behaviors.

Deliverable: Accessibility UAT | Dependency: M16.1 | Owner: TBD

M16.6  Record defects in GitHub Issues with severity and acceptance criteria.

Deliverable: UAT defect log | Dependency: M16.1 | Owner: TBD

M16.7  Resolve release-blocking defects.

Deliverable: UAT remediation | Dependency: M16.6 | Owner: TBD

M16.8  Obtain CommuniCare content and visual approval.

Deliverable: CommuniCare signoff | Dependency: M16.7 | Owner: TBD

M16.9  Obtain Cumberland County ITS technical/deployment approval.

Deliverable: ITS signoff | Dependency: M16.7 | Owner: TBD

## M17 - Domain, HTTPS, and Production Cutover

M17.1  Document existing DNS records before any change.

Deliverable: DNS backup record | Dependency: M0.8 | Owner: TBD

M17.2  Verify the custom domain in GitHub before cutover.

Deliverable: Verified custom domain | Dependency: M14.7 | Owner: TBD

M17.3  Configure the custom domain in GitHub Pages settings.

Deliverable: Pages custom domain | Dependency: M17.2 | Owner: TBD

M17.4  Configure the required apex and/or www DNS records according to the approved domain pattern.

Deliverable: DNS configuration | Dependency: M17.3 | Owner: TBD

M17.5  Do not use wildcard DNS records for the Pages domain.

Deliverable: DNS security control | Dependency: M17.4 | Owner: TBD

M17.6  Allow DNS and certificate provisioning time and monitor status.

Deliverable: Propagation monitoring | Dependency: M17.4 | Owner: TBD

M17.7  Enable Enforce HTTPS after GitHub reports the domain/certificate as ready.

Deliverable: HTTPS enforcement | Dependency: M17.6 | Owner: TBD

M17.8  Validate both apex and www behavior as applicable.

Deliverable: Domain validation | Dependency: M17.7 | Owner: TBD

M17.9  Run production smoke tests for navigation, assets, documents, canonical links, redirects, and HTTPS.

Deliverable: Production smoke test | Dependency: M17.7 | Owner: TBD

M17.10  Validate that no mixed-content HTTP resources remain.

Deliverable: HTTPS validation | Dependency: M17.9 | Owner: TBD

M17.11  Keep documented rollback DNS values and prior site deployment available until stabilization is complete.

Deliverable: Rollback readiness | Dependency: M17.1 | Owner: TBD

## M18 - Post-Go-Live and SLA Operations

M18.1  Establish uptime monitoring for the production URL.

Deliverable: Monitoring configured | Dependency: M17 | Owner: TBD

M18.2  Establish broken-link monitoring or scheduled link checks.

Deliverable: Link monitoring | Dependency: M17 | Owner: TBD

M18.3  Define incident severity and response expectations according to the SLA.

Deliverable: Support matrix | Dependency: M17 | Owner: TBD

M18.4  Document content change request process.

Deliverable: Content support procedure | Dependency: M17 | Owner: TBD

M18.5  Document emergency publishing process.

Deliverable: Emergency change procedure | Dependency: M17 | Owner: TBD

M18.6  Document repository access onboarding and offboarding.

Deliverable: Access procedure | Dependency: M1 | Owner: TBD

M18.7  Schedule periodic dependency and GitHub Actions review if a build toolchain is used.

Deliverable: Dependency maintenance schedule | Dependency: M6 | Owner: TBD

M18.8  Schedule periodic accessibility review after significant design/content changes.

Deliverable: Accessibility maintenance schedule | Dependency: M15 | Owner: TBD

M18.9  Schedule periodic content review with CommuniCare.

Deliverable: Content review cadence | Dependency: M3 | Owner: TBD

M18.10  Document backup/restore strategy for the repository and released site artifacts.

Deliverable: Recovery procedure | Dependency: M1, M14 | Owner: TBD

## M19 - Legacy Retirement and Archive

M19.1  Confirm the new GitHub Pages site is stable for the agreed stabilization period.

Deliverable: Stabilization approval | Dependency: M18 | Owner: TBD

M19.2  Archive or preserve the legacy repository according to County retention requirements.

Deliverable: Legacy source archive | Dependency: M19.1 | Owner: TBD

M19.3  Preserve a final copy of the old site and its important documents before removal.

Deliverable: Legacy site package | Dependency: M19.1 | Owner: TBD

M19.4  Retire the old web hosting only after rollback is no longer required.

Deliverable: Legacy hosting retirement | Dependency: M19.1-M19.3 | Owner: TBD

M19.5  Remove obsolete DNS or hosting records only after verification.

Deliverable: Infrastructure cleanup | Dependency: M19.4 | Owner: TBD

M19.6  Close the project with final documentation, approvals, and outstanding enhancement backlog.

Deliverable: Project closeout | Dependency: M19.5 | Owner: TBD

# 9. Dependency Map

| Dependency | Required Before | Why It Matters |
| --- | --- | --- |
| Static/public-only architecture approval | Development | Determines whether GitHub Pages is appropriate. |
| Repository ownership and plan confirmation | Pages setup | Determines repository visibility and hosting eligibility/cost. |
| CommuniCare content decisions | Full migration | Developers cannot know which legacy content remains valid. |
| Approved sitemap | Page build-out | Prevents rework in navigation and URLs. |
| Approved visual/accessibility design system | Component development | Creates consistent implementation rules. |
| Domain/DNS ownership | Production cutover | Custom domain cannot be moved without authorized DNS access. |
| GitHub branch/deployment controls | Production publishing | Prevents unauthorized or unreviewed changes. |
| Accessibility remediation | Production approval | Release should not knowingly ship critical accessibility defects. |
| UAT/content signoff | Domain cutover | Prevents replacing the current site before CommuniCare approves content. |
| Rollback record | DNS change | Enables recovery if production cutover fails. |

## 9.1 Critical Path

Confirm static-site scope and GitHub Pages eligibility.

Create/secure repository.

Complete legacy and content inventory.

Obtain CommuniCare content decisions.

Approve sitemap and design system.

Build static foundation and global components.

Build and migrate content.

Configure automated checks.

Deploy to GitHub Pages preview/default URL.

Complete accessibility validation.

Complete CommuniCare UAT and signoff.

Verify domain and prepare DNS rollback.

Cut over custom domain and enforce HTTPS.

Monitor stabilization period.

Retire legacy hosting.

# 10. Risk Register

| ID | Rating | Risk | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | High | A new requirement introduces sensitive data or server-side processing after static architecture is approved. | Scope expansion and redesign. | Freeze base requirements early. Treat dynamic features as a separate architecture decision. |
| R-02 | High | Repository accidentally contains secrets, internal configuration, or non-public files. | Security exposure. | Assume repository contents are public. Use review, secret scanning, and repository hygiene. |
| R-03 | High | CommuniCare content is outdated or conflicting. | Incorrect public information. | Require named content owners and written approval. |
| R-04 | High | Accessibility defects remain at launch. | ADA/WCAG risk and poor user experience. | Use automated and manual testing, plus remediation before signoff. |
| R-05 | Medium | PDFs or other legacy documents are inaccessible. | Accessibility risk. | Remediate, replace with HTML, or document approved exception/remediation plan. |
| R-06 | High | DNS is changed incorrectly during cutover. | Website outage. | Record current values, lower TTL if appropriate/approved, verify domain first, maintain rollback plan. |
| R-07 | High | Custom domain is not verified or wildcard DNS creates takeover exposure. | Domain/security risk. | Verify domain and avoid wildcard DNS records. |
| R-08 | Medium | GitHub Pages service disruption occurs. | Public site unavailable. | Use uptime monitoring and document hosting limitations in SLA/operational expectations. |
| R-09 | Medium | GitHub account or maintainer account is compromised. | Unauthorized site changes. | MFA, least privilege, branch protection, PR review, audit/change history. |
| R-10 | Medium | Third-party GitHub Action becomes compromised or changes behavior. | Build/deployment supply-chain risk. | Minimize third-party actions, pin/manage versions, review workflow changes. |
| R-11 | Medium | Broken legacy external links are migrated unchanged. | Poor UX and credibility. | Run link audit and require content-owner decision. |
| R-12 | Medium | URL changes damage bookmarks/search ranking. | SEO/user impact. | Preserve paths where practical, create redirects where supported by site design, maintain migration matrix. |
| R-13 | Medium | Large media or documents degrade performance. | Slow site, mobile impact. | Optimize images, audit document size, run performance checks. |
| R-14 | Medium | Content editors modify markup without accessibility knowledge. | Accessibility regression. | Use reusable components/content patterns and PR checklist. |
| R-15 | Medium | Repository plan or visibility changes create unexpected Pages cost/eligibility changes. | Hosting or budget impact. | Confirm GitHub plan and repository visibility before go-live. |
| R-16 | Low | A client-side script fails. | Limited interactive feature impact. | Progressive enhancement. Core content/navigation must work without nonessential JavaScript. |
| R-17 | Medium | Custom analytics or embeds create privacy/accessibility/performance issues. | Compliance and UX impact. | Approve third-party services before implementation. |
| R-18 | Medium | CommuniCare requests an online contact form after design is complete. | Architecture change. | Evaluate approved external service or separate backend; do not add insecure browser-only processing. |
| R-19 | Medium | Legacy site is retired too quickly. | Difficult rollback or lost content. | Preserve old site and repo until stabilization approval. |
| R-20 | Low | GitHub Pages bandwidth/build limits become relevant. | Service limitation. | Monitor usage and reassess hosting if traffic or build frequency materially changes. |

# 11. Codex Implementation Strategy

Codex should be used in controlled work packages. Do not ask Codex to 'rewrite the whole site' in one prompt. Each work package should be tied to an approved milestone, should modify a bounded set of files, should run the required tests, and should finish with a pull request or reviewable commit.

## 11.1 Standard Codex Prompt Header

### Reusable prompt header

You are working in the CommuniCare modern website repository. Read AGENTS.md, README.md, docs/architecture.md, docs/accessibility.md, and the relevant milestone document before changing files. This is a static public-information website deployed to GitHub Pages. Do not add a backend, database, authentication, secrets, server runtime, or direct data-processing service unless the task explicitly includes an approved architecture change. Target WCAG 2.2 Level AA. Prefer semantic HTML. Use ARIA only when native HTML cannot express the required semantics. All functionality must be keyboard accessible. Preserve responsive behavior and support zoom/reflow. Do not migrate legacy ASP.NET/VB.NET code. Migrate only approved public content. Run all build, lint, link, and accessibility checks before completing the task. Do not modify unrelated files. Summarize changed files, tests run, known issues, and any decisions that require human approval.

## 11.2 Recommended Codex Work Packages

| Work Package | Purpose | Related Milestone |
| --- | --- | --- |
| WP-01 | Documentation and repository baseline | M0-M1 |
| WP-02 | Legacy content inventory and URL map | M2 |
| WP-03 | Static project scaffold | M6 |
| WP-04 | Design tokens and accessibility foundation | M5-M6 |
| WP-05 | Header, navigation, footer, breadcrumbs, announcement | M7 |
| WP-06 | Homepage | M8 |
| WP-07 | Program/service content model and template | M9 |
| WP-08 | Batch migration of approved program pages | M9 |
| WP-09 | Resources and document library | M10 |
| WP-10 | Contact and location page | M11 |
| WP-11 | SEO, sitemap, robots, social metadata | M12 |
| WP-12 | Automated PR quality workflow | M13 |
| WP-13 | GitHub Pages deployment workflow | M14 |
| WP-14 | Accessibility defect remediation batch | M15 |
| WP-15 | UAT defect remediation | M16 |
| WP-16 | Production/domain documentation and runbook | M17-M18 |

## 11.3 Example: Homepage Codex Prompt

### WP-06 sample

Implement the approved CommuniCare homepage. Use the approved design tokens and existing shared components. Requirements: - One H1 only. - Hero copy must come from the approved content source. Do not invent organization claims. - Primary actions must use descriptive link text. - Program/service cards must use semantic heading levels and real links. - Images must have approved alt text or be marked decorative. - No carousel unless explicitly approved. - No auto-playing media. - All motion must respect prefers-reduced-motion. - Keyboard order must match visual/logical reading order. - Layout must reflow at 320 CSS pixels without horizontal scrolling except for allowed content types. - Verify at 200% zoom. - Run build, lint, link, and accessibility checks. Return a summary of files changed and any content questions. Do not modify other page content.

## 11.4 Example: Content Migration Codex Prompt

### WP-08 sample

Migrate only the program pages marked APPROVED in docs/content-inventory.md. For each approved program: - Preserve factual content unless an approved replacement is provided. - Remove legacy table-based layout, image navigation, ASP.NET directives, server controls, and duplicated header/footer markup. - Use the shared Program/Service template. - Preserve meaningful legacy URLs when practical or add the path to the migration map. - Use semantic lists and headings. - Convert 'click here' links into descriptive link text. - Do not migrate obsolete referral handlers or orphaned forms. - Flag any questionable or conflicting content instead of guessing. Run the full validation suite after migration.

# 12. Accessibility Acceptance Checklist

| Area | Acceptance Criterion |
| --- | --- |
| Page structure | Correct language, title, landmarks, one logical H1, heading hierarchy. |
| Keyboard | Every control reachable and operable; no keyboard traps. |
| Focus | Visible focus indicator and logical order. |
| Navigation | Skip link, consistent menus, clear current location. |
| Links | Purpose understandable from link text/context; no ambiguous repeated 'click here' links. |
| Images | Meaningful alt text; decorative images ignored appropriately. |
| Color | Required text/non-text contrast; meaning not conveyed by color alone. |
| Zoom/reflow | Usable at 200% zoom and narrow viewport without loss of content or function. |
| Motion | Reduced-motion preference respected. |
| Forms | If any approved form is later introduced, labels, instructions, errors, and status messages must be accessible. |
| Documents | Public PDFs/documents reviewed for accessibility or replaced/supplemented with accessible HTML as required. |
| Media | Captions/transcripts provided where applicable. |
| Automated testing | No unresolved release-blocking automated findings. |
| Manual testing | Keyboard and representative screen-reader testing completed. |

# 13. GitHub Pages Production Deployment Runbook

Confirm all production changes are merged to the approved production branch.

Confirm required quality checks passed.

Confirm CommuniCare UAT signoff.

Confirm Cumberland County ITS technical signoff.

Confirm custom domain ownership and DNS access.

Record all current DNS records and TTL values.

Verify the custom domain in the appropriate GitHub account/organization.

Configure the custom domain in repository Pages settings.

Apply the required DNS records for the approved apex/www design.

Monitor DNS propagation and GitHub Pages domain status.

Wait for TLS certificate provisioning.

Enable Enforce HTTPS.

Verify HTTP redirects to HTTPS.

Verify apex and www behavior.

Run production smoke tests.

Run a production accessibility spot check.

Verify sitemap.xml and robots.txt.

Verify all critical documents and external links.

Verify uptime monitoring.

Record the release tag/commit and production time.

Begin the stabilization period.

## 13.1 Rollback

Code rollback: redeploy or revert to the last approved release/commit.

DNS rollback: restore the recorded previous DNS values if the cutover itself caused the outage.

Content rollback: revert the specific content commit.

Keep the prior hosting environment available until the stabilization period is formally closed.

Document who has authority to order an emergency rollback.

# 14. Ongoing Support Under the SLA

## 14.1 Standard Content Change

Receive the approved content request.

Confirm requestor authority and content ownership.

Create GitHub issue/change record.

Create a branch.

Make the content change using established components and accessibility rules.

Run local/automated checks.

Open pull request.

Review content, accessibility, and visual impact.

Merge after approval.

Allow GitHub Pages deployment workflow to publish.

Verify the live page.

Close the issue with the deployed commit/release reference.

## 14.2 Emergency Change

Emergency changes should still be committed and traceable. The SLA may allow an expedited review path, but the project should not encourage direct untracked edits. Define the approver, severity criteria, validation minimums, and post-change review before go-live.

## 14.3 Routine Maintenance

Review dependencies and build tools periodically.

Review GitHub Actions versions and permissions.

Review collaborator access and remove users who no longer need write access.

Review content for stale dates, staff names, contact information, and broken links.

Review accessibility after significant content/design changes.

Review uptime and Pages incidents.

Keep a clean release history and change log.

# 15. Hosting and Cost Considerations

GitHub Pages is available for public repositories on GitHub Free and GitHub Free for organizations. It is also available for public and private repositories on eligible paid GitHub plans. The final hosting cost therefore depends on the repository visibility and the GitHub plan attached to the owning account or organization.

If the modern site repository is public and the account/organization remains eligible for GitHub Pages under GitHub Free, there may be no separate GitHub Pages hosting charge.

Domain registration and DNS services are separate from GitHub Pages and remain the responsibility of the domain owner.

Any optional third-party analytics, forms, monitoring, or accessibility services may introduce separate cost.

Cumberland County staff time for development and SLA support remains an operational cost even if hosting itself has no separate charge.

GitHub pricing and product terms should be rechecked before production approval because service plans can change.

# 16. Go-Live Readiness Checklist

| Area | Required Before Cutover |
| --- | --- |
| Scope | No unapproved dynamic/sensitive requirement has been introduced. |
| Content | CommuniCare approved all production content. |
| Repository | Permissions and branch protections reviewed. |
| Build | Production build succeeds from clean checkout. |
| Quality | Required automated checks pass. |
| Accessibility | Release-blocking accessibility findings remediated. |
| Links | No critical broken internal links. |
| Documents | Approved documents published and reviewed. |
| SEO | Titles, descriptions, sitemap, robots, canonicals complete. |
| Domain | Domain verified and DNS plan approved. |
| Rollback | Previous DNS and previous site available. |
| HTTPS | Certificate provisioned and Enforce HTTPS ready. |
| Monitoring | Uptime check ready. |
| UAT | CommuniCare signoff received. |
| ITS | Technical signoff received. |

# 17. Future Enhancement Decision Rules

The static architecture should remain intentionally simple. Future requests should be evaluated by the following rule: if the feature requires trusted server-side execution, confidential data, authentication, a secret key, protected storage, or a database, do not implement it directly in GitHub Pages.

| Future Request | Static Site? | Recommended Direction |
| --- | --- | --- |
| New public text/page | Yes | Add to static content. |
| New public PDF/resource | Yes | Add after content/accessibility review. |
| Public announcement | Yes | Use static announcement component/content. |
| Client-side filtering of public resources | Yes | Use accessible JavaScript, if needed. |
| Contact email link | Yes | Use approved public mailto address. |
| Embedded map | Yes, with review | Provide equivalent text address/location details. |
| Public contact form | Not by itself | Use separately approved form service or backend after privacy/security review. |
| Secure referral form | No | Separate application/backend. |
| User login | No | Separate application/backend. |
| Database-backed program management | No | Use CMS/backend or separate app. |
| Protected document upload | No | Separate application/backend. |
| Online payment | No | Approved external payment service or separate application. |

# 18. Reference Sources

The following official GitHub documentation should be used during implementation. Links were current when this plan was prepared and should be rechecked before production cutover.

GitHub Pages quickstart: https://docs.github.com/en/pages/quickstart

Configuring a publishing source: https://docs.github.com/en/pages/getting-started-with-github-pages/configuring-a-publishing-source-for-your-github-pages-site

Using custom workflows with GitHub Pages: https://docs.github.com/en/pages/getting-started-with-github-pages/using-custom-workflows-with-github-pages

Managing a custom domain: https://docs.github.com/en/pages/configuring-a-custom-domain-for-your-github-pages-site/managing-a-custom-domain-for-your-github-pages-site

Verifying a custom domain: https://docs.github.com/en/pages/configuring-a-custom-domain-for-your-github-pages-site/verifying-your-custom-domain-for-github-pages

Securing a Pages site with HTTPS: https://docs.github.com/en/pages/getting-started-with-github-pages/securing-your-github-pages-site-with-https

# Appendix A - Master Task Checklist

Use this appendix as the high-level project tracking list. Detailed acceptance criteria remain in the milestone sections.

| ID | Milestone | Status | Owner | Target |
| --- | --- | --- | --- | --- |
| M0 | Project Initiation and Architecture Confirmation | Not Started | TBD | TBD |
| M1 | Repository and GitHub Controls | Not Started | TBD | TBD |
| M2 | Legacy Site Inventory | Not Started | TBD | TBD |
| M3 | Content and Requirements Validation | Not Started | TBD | TBD |
| M4 | Information Architecture | Not Started | TBD | TBD |
| M5 | Accessibility and Design System | Not Started | TBD | TBD |
| M6 | Static Site Foundation | Not Started | TBD | TBD |
| M7 | Core Navigation and Global Components | Not Started | TBD | TBD |
| M8 | Homepage | Not Started | TBD | TBD |
| M9 | Program and Service Content | Not Started | TBD | TBD |
| M10 | Resources, Documents, and Public Information | Not Started | TBD | TBD |
| M11 | Contact and Location Experience | Not Started | TBD | TBD |
| M12 | SEO, Performance, and Metadata | Not Started | TBD | TBD |
| M13 | Automated Quality Gates | Not Started | TBD | TBD |
| M14 | GitHub Pages Deployment | Not Started | TBD | TBD |
| M15 | Accessibility Validation and Remediation | Not Started | TBD | TBD |
| M16 | User Acceptance Testing | Not Started | TBD | TBD |
| M17 | Domain, HTTPS, and Production Cutover | Not Started | TBD | TBD |
| M18 | Post-Go-Live and SLA Operations | Not Started | TBD | TBD |
| M19 | Legacy Retirement and Archive | Not Started | TBD | TBD |

# Appendix B - Codex Definition of Done

Task scope matches the assigned work package.

No unrelated files changed.

No secrets, credentials, internal-only values, or protected data added.

Static build succeeds from a clean checkout.

Output is deployable to GitHub Pages.

HTML is semantic and accessibility rules are followed.

Keyboard behavior is tested for affected interactive components.

Responsive behavior is tested.

Automated quality checks pass.

Links introduced by the change are valid.

Content questions are flagged rather than guessed.

Documentation is updated when behavior, architecture, build, or deployment changes.

Codex provides a concise summary of files changed and tests executed.

# Appendix C - Items Removed From the Prior Server-Hosted Plan

The following items are not required for the base static GitHub Pages implementation and should not be added unless future approved requirements justify them:

DMZ IIS web server for the public site.

.NET 10 web runtime hosting.

Blazor server-side application.

Telerik UI for Blazor.

Entity Framework Core.

SQL Server database for public content.

Database connection strings.

Windows service account or SQL login for the website.

Server-side SMTP for the website.

Application pool configuration.

IIS deployment pipeline.

Do not overbuild: The success criterion is not to reproduce the old technology on a newer stack. The success criterion is to deliver the approved public content in a modern, accessible, secure, maintainable static website. Add backend technology only when an approved requirement needs it.